## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations required for doing project
|  | 2 | LLM for Contract analysis
|  | 3 | Clause Identification and Risk Analysis Engine
|  | 4 | Update tracking and Contract Modification

## Sprint Backlog
]
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | DDd
[8 empty] | 0 | 46381 | 0 | 0 | 0 | 46386 | 46387 | 46023 | 46024 | 46025 | 46026 | 46027 | 46028 | 46029 | 46030
SPRINT 1 BACKLOG
1 |  | Foundations required for doing project | Nov 10th | Nov 24th |  | Learnt and practiced all the fundamentals required for project | Done |  | Nov 10th | Nov 11th | Nov 12th | Nov 13th | Nov 14th | Nov 15th | Nov 16th | Nov 17th | Nov 18th | Nov 19th | Nov 20th | Nov 21th | Nov 22nd | Nov 23rd
|  | Foundations required for doing project | Nov 10th | Nov 24th | Gulsan Ram | Learnt and practised all fundamentals required for project | Done |  | introduction session | Install python and notebook and introduction to the python | learnt about the python keyword and naming convention | learnt about the variables and agile sheet and what are condition for getting the intership completion certificates | data types and different ways to store values in variables | Revisied the topics | revise the topic covered | Discussion about range().function and its cases ,if flow control | loops and functions | fpython function and their types | learnt modules and keyword | oops concept | constructor and instance variables | revised the topics
|  | Foundations Required for doing Project | Nov 10th | Nov 24th | Sunkara Bhanu Pavan Kalyan | Learnt and practiced all the fundamentals required for project | Done |  | introduction session | learnt to install the python and the jupyter notebook | learnt about python keywords and naming conventions | Learned about Variables and how to operate on the agile sheet | leant about variables and data structures like lists,tuples,dictionaries in detail | revised about python keywords,variables | revised about tuples and dictionaries | learnt about range(),mutable & immutable, control statements like if,elif,else and conditional statements | learnt about flow control (loops) and functions | learnt about functions with return keyword, arguments and its types | learnt about modules and keywords like import, as, from | learnt about the oops concepts in detail | learnt about the constructors and instance variables | practised about the constructors and functions concepts
1 |  | Foundations Required for doing Project | Nov 10th | Nov 24th | Sai Amar Durgesh Kopparapu | Completely understood the basics of the AI Compliance Checker project. | Done |  | Introduction Class | Installing Python and Jupyter Notebook | Python keywords and Naming Conventions | Knowing about Naming Conventions and about filling of the Agile Sheet | Data Structures (Lists, Tuples, Dictionary) | Revision and practice | Revision and practice | range() function with use cases | Functions and flow controls | Learnt about functions and also return keywords, arguments | Learnt about the modules and keyword | OOPS | OOPS (Constructor & Instance Variables) | Revised the topics
1 |  | Foundations Required for doing Project | Nov 10th | Nov 24th | Charishma Maliga | Understood the basics concepts Required for the Project | Done |  | Introduction for the Internship | Installed Python and Jupyter Notebook on the PC | Keywords, Naming Conventions in Python | Variables in Python and Agile sheet Filling | Multi Variables and Datatypes | Revised the topics covered till now | Revised the topics covered till now | Range, Mutable and Immutable, conditional Flow control | Flow controls and Functions | Functions with return keyword, Arguments and its types | Module (Import, as, from keywords) | Oop's concept | Object, Constructor and Instance variables | Practised the topics covered in this week
1 |  | Foundations required for doing project | Nov 10th | Nov 24th | Domakonda Anirudh | Learnt about fundamentals required for project | Done |  | Introduction session | installation of python and jupyter | Learned Python variables, keywords | Learned about variables and how to work on the agile sheet | DataTypes and multivariables | Revised and practiced previous topics | Revised all concepts covered | Range, Mutable and unmutable data, flow control | Loops and functions | Functions (return keyword, Arguments and types) | learnt about modules and keywords | Learnt about OOPS concepts | Constructor and Instance variables | Revision
1 |  | Foundations Required for doing Project | Nov 10th | Nov 24th | Atmakuri Bhuvanesh | Learnt about fundamentals required for project | Done |  | Introduction session | Installation of python and jupyter | Variables,words,Keywords | Variables and how to operate on the agile sheet | DataTypes and multivariables | Practiced jupyter notebook | Revised all the concepts | Range, Mutable and unmutable data, flow control | Loops and types of functions | Learnt about Functions with return keyword, arguments and types | learnt about modules and keywords | Learnt about OOPS concepts | Object, Constructor and Instance variables | Revision
1 |  | Foundations required for doing project | Nov 10th | Nov 24th | Tanishq Navsariwala | Learnt about fundamentals required for project | Done |  | Inroductory Session | Installation of Python and Jupyter Notebook | Learned Naming Conventions and Python Keywords | Learned about Variables and how to operate on the agile sheet | Multi Variables and Datatypes | Practiced all previous session topics | practiced all topics covered in previous session | learnt about range(),mutable & immutable, control statements | Flow controls and functions | Learnt about Functions with return keyword, arguments and types | learnt about modules and Keywords | learnt about oops concept | constructors and instance variables | revision
|  | Foundations required for doing project | Nov 10th | Nov 24th | Tanisha Bhardwaj | practiced all fundamentals required for project | Done |  | Introduction Session | Python and Jupyter Installation done | Brief Knowledge about keywords and naming conventions | Understanding about variables and how to work on agile sheet | Understanding of storing values in variables in different ways, knowledge about data types and different data structures. | revision of data structures and its use cases | Revision of all previous topics | Brief discussion about range data type and function and its use cases with immutable and mutable type and flow control and conditonal statements usecases | Understanding about loops and functions | brief discussion on functions and its types | Brief discussion on import, from and as kewords | Brief discussion on oops concepts | Different types of constructors | Revision on previous topics
1 |  | Foundations required for doing project | Nov 10th | Nov 24th | Omkar Gaware | Learnt and practiced all the fundamentals required for project | Done |  | Introduction Session | installation of python and jupyter | Keywords, Naming Conventions | variables and how to fill agile sheets, project criterias | Understanding types of Data Structures-String, list ,tuple,set ,dict | Revised and practiced previous topics | Revised all the concepts | learnt about range(),mutable & immutable, control statements | Loops and functions in python | Functions with return keyword, Arguments and its types | learnt modules and keyword | OOPS Concepts | Object, Constructor and Instance variables | Rivision
|  | Foundations required for doing project | Nov 10th | Nov 24th | Deeepak Sharma |  | Done |  | Nov 10th: introduction session; Nov 11th: installation of python and jupyter; Nov 12th: Python keywords and Naming Conventions; Nov 13th: Learned about variables and how to work on the agile sheet
|  | Foundations required for doing project | Nov 10th | Nov 24th | Yashovardhan Thopte | Learnt and practiced all the fundamentals required for project | Done |  | Introduction Session | Installation of Python and Jupyter | Python Keywords, Identifiers and other conventions | Brief detail on Variables and how to operate on the agile sheet | Data Structures | Revision of everything | Revision | Range, Mutable and unmutable data, flow control | Different types of loops | Studied about Functions in python | Studied about modules in python | Object Oriented Programming | Constructors In Python | Revision
|  | Foundations Required for doing Project | Nov 10th | Nov 24th | Chinthala Keerthi | Practiced all the fundamentals required for the project | Done |  | introduction session | installation of python and jupyter | Python Keywords,Naming convention | understanding Variables and how to operate on the agile sheet | Multi Variables and Datatypes | Practiced all previous session topics | Practiced all topics covered in previous session | learnt about range(), Mutable and immutable data, if flow control | Flow controls and functions | Learnt about Functions with return keyword, arguments and types | learnt about modules and Keywords
1 |  | Foundations required for doing project | Nov 10th | Nov 24th | Sujit Yadav | Learnt and practice all the fundamentals foe the Project | Done |  | Introduction Session | Installation of Python and Jupyter Notebook | Naming Conventions ,Identifier,Rules for Identifers,Keywords | Variables, How to operate on aglile sheet | Understanding types of Data Structures-String, list ,tuple,set ,dict and Types of data | Revision of variables,Identifiers | Revision of Data Structures | Range,Mutable and Immutable data, flow control | python functions | Function with return keyword,Types of Arguments | Python Modules | Object Oriented Programming in python | Constructors and Instance Variable | Revision
|  | Foundations required for doing project | Nov 10th | Nov 24th | Rudraprasad Khatua | Practiced all the fundamentals required for the project | Done |  | Introduction about the project | Installation of Python and Jupyter Notebook | Naming Conventions ,Identifier,Rules for Identifers,Keywords | Variables, How to operate on aglile sheet | Understanding types of Data Structures-String, list ,tuple,set ,dict and Types of data | Revision | Revision | Range, Mutable and unmutable data, flow control | for and while loop and function in python | Function with return keyword,Types of Arguments | Python Modules
1 |  | Foundations required for doing project | Nov 10th | Nov 24th | Siddireddi Shanmukha Sanjana | Learnt and Practiced all the fundamentals required for the project | Done |  | Introduction Session | Python and Jupyter Installation | Python Keywords and Naming Conventions | Python Variables | Python Data Types | Revised variables, Named Keywords | Revised Sets, Dictionaries, List, and Tuples | Range(), Mutable, Immutable, and Flow Controls | Flow control and Functions | Python Functions and their types | Python Modules | Python OOPS | Constructors, and Instance Variables | Revised Constructors
|  | Foundations required for doing project | Nov 10th | Nov 24th | Moitrayan Nath | Learnt about fundamentals required for the project | Done |  | Introductory Session | Python and Jupyter Installation done | Python keywords and Naming Conventions | Python Variables | Python Data Types | Revision | Revision | Range, Mutable and Immutable, conditional Flow control | Flow controls and functions | Functions with return keyword, Arguments and its types | Python Modules | OOPS Concepts | Constructor and Instance variables | Revision
|  | Foundations required for doing project | Nov 10th | Nov 24th | Tammina Varaha Venkata Prasad | Learnt about fundamentals required for the project | Done |  | Introduction Session | Python and Jupyter Installation done | Learnt about Keywords and naming conventions | Learned about variables and Agile sheet filling | Multi Variables and Datatypes | Revised and practiced previous topics | Revised all the concepts covered | learnt about range(),mutable& immutable,control statements | learnt about loops and types of functions | learnt about functions with return keyword,arguments and types | learnt about modules and keywords | learnt about oops concepts | Constructors and instance variables | Revision
1 |  | Foundations Required for doing Project | Nov 10th | Nov 24th | Rohith Vunna | understood all the fundamentals required for the project | Done |  | introduction session | installation of python and jupyter | Python Keywords,Naming convention and rules for identifiers | understanding Variables and how to fill on the agile sheet | understanding Multi Variables and Datatypes | Revising previous session topics | Practiced all topics covered in previous session | learnt about range, Mutable and immutable data, 'if' flow control | Flow controls and functions in python | Functions with return keyword, arguments and types | learnt about modules and Keywords | OOPS in python | Constructors, and Instance Variables in python | Revision
1 | 1 | Foundations Required for doing Project | Nov 10th | Nov 24th | Dodde Raju | Practiced all the fundamentals required for the project | Done |  | Introduction about the project | Installation of Python and Jupyter Notebook | Keywords and Naming Conventions in Python | Varialbles in Python and Agile sheet filling | Python Data Types | Revised variables, Keywords | Practiced all topics covered in previous session | Range,Mutable and Immutable data, flow control | Flow Controls and Functions | Functions with return keyword, Arguments and its types | learnt about modules and Keywords | Object Oriented Programming in Python | Constructors and Instance Variables | Revised constructors and Functions
1 |  | Foundations Required for doing Project | Nov 10th | Nov 24th | Manini Ojha | understood all the fundamentals required for the project | Done |  | introduction about the project | Python and Jupyter Notebook installation | Keywords and Naming Conventions for Identifiers in Python | Understanding about variables and how to work on agile sheet | Python Data Types | practiced variables and keywords | Revision of topics covered | learnt about range, Mutable and immutable data, 'if' flow control | Flow Controls and Functions | Function with return keyword,Types of Arguments | Python Modules | OOPS Concepts | Constructors and Instance Variables | Revised constructors and Functions
In
2 |  | LLM for Contract analysis | Nov 25th | Dec 9th | Charan | Column 1 | Done |  | Nov 24th | Nov 25th | Nov 26th | Nov 27th | Nov 28th | Nov 29th | Nov 30th | Dec 1st | Dec 2nd | Dec 3rd | Dec 4th | Dec 5th | Dec 6th | Dec 7th
2 |  | LLM for Contract analysis | Nov 25th | Dec 9th | Domakonda Anirudh | Understood about the project, LLM and Executed Demo codes | Done |  | Project Understanding | Presentation about project | Virtual Environment Creation | Intro to fundamentals | Presentation on project | Practised Python Concepts | Practiced concepts of this week | Prompt Engineering | DS, AI, and Gen AI | Learned about LLM and implemented Groq_key open source | Explanation and Execution of Demo codes | Packages and Workflow for next Milestone | Revision Package | Revision
2 |  | LLM for Contract analysis | Nov 25th | Dec 9th | Sunkara Bhanu Pavan kalyan | Understood about the project, LLM and Executed Demo codes | Done |  | project discussion | presenting what we understood from the project | learnt about how to create the virtual environment in detail and in practical | introduction for the tech tools what we should required in this project | project discussion from the students for the betterment | practised the creation of virtual environment | practised the concepts in python | learnt about the prompt engineering and how it is useful in our project | Learnt about the difference between Data Science, AI and Gen AI and also the Fundamentals of LLM | learnt about LLM Fundamentals and Groq API key creation and usecase | learnt about the codes execution in detail | learnt about the packages and workflow of milestone 2 | revised the packages concept | tried the execution of the project
2 |  | LLM for Contract analysis | Nov 25th | Dec 9th | Charishma Maliga | Understood about LLM and Executed some demo codes | Done |  | Understanding the Project | Quick Overviews of the team members about what they Understood about the project | Virtual Environment Creation | Introduction of Tech tools | Shared Team members understanding about the Project | Practised Python Concepts | Practised this week topics | Prompt Engineering | Difference between Data Science, AI and Gen AI and also the Fundamentals of LLM | LLM Fundamentals and Groq API key | Explanation and Execution of Demo codes | Packages and Workflow for next Milestone | Revised and Practised Prompt Engineering | Executed demo codes
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Siddireddi Shanmukha Sanjana | Understood about the project, LLM and Executed Demo codes | Done |  | Project Understanding | Presentation about project | Creation of Virtual Environment | Introduction of Tech tools | Project Presentation Session | Revised Python Concepts | Practiced Python Concepts | Prompt Engineering | Data Science,AI,GenAI,LLM | LLM and Creation of Groq API key | Groq API implementation | Package and Workflow for Milestone 2 | Revised Prompt Engineering | Revised Packages
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Deepak sharma |  | Done |  | Understanding the Project | Presentation about Project understanding | Virtual Environment Creation | Introduction to Tech Tools | Project Presentation | Revised Concepts about Python | Revised Concepts | Prompt Engineering | AI and GEN AI
2 |  | LLM For Contract Analysis | Nov 25th | Dec 9th | Tanishq Navsariwala | Understood about the project, LLM and Executed Demo codes | Done |  | Overview of The Project | Presentation about Project understanding | Virtual Environment Creation | Introduction to Tech Tools | Presentation Session #2 | Revised Concepts about Python | Revised OOPS | Overview of Prompt Engineering | LLM Fundamentals | LLM Fundamentals and Groq API key | Explanation and Execution of Demo codes | Introduction to Packages | Revised | Revised Packages
|  | LLM for Contract Analysis | Nov 25th | Dec 9th | Chinthala Keerthi | understood about LLM and Demo Codes execution | Done |  | Project Understanding | Presentation about Project understanding | Virtual Environment Creation | Introduction to Tech Tools | interactive session about project understanding | Revised Concepts about Python | practiced all previous session topics | overview of promp engineerung and how to use prompt | DS, AI, and Gen AI | LLM Fundamentals and Groq API key | Explanation and Execution of Demo codes | introduction to Packages and workflow for milestone-2 | Practiced demo codes | revised about previous session topics
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Rohith Vunna | Understood about Project, executed some demo codes. | Done |  | Project Discussion | Presentation about Project understanding | how to createVirtual Environment in detail | introduction to Tech Tools required for this project | Presentation about Project | Creating virtual environment | Revised previous comcepts | overview about prompt engineering | Gen AI and AI | learnt about LLM fundamentals and API key generation | Demo codes are Explained and execute | learnt about Packages and workflow of milestone-2 | practiced demo codes from beginning of the process | revised about python
|  | LLM for Contract Analysis | Nov 25th | Dec 9th | Moitrayan Nath | Understood about Project, executed some demo codes. | Done |  | Project Understanding | Presentation about project | Virtual Environment Creation | Introduction to Tech Tools | Project Presentation | Revised Concepts about Python | Practiced concepts of this week | Prompt Engineering | DS, AI, and Gen AI | Learned about LLM and implemented Groq_key open source | Explanation and Execution of Demo codes | Packages and Workflow for next Milestone | Revision Package | Revised Packages
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Dodde Raju | Hands on Practice with Some Demo Codes | Done |  | Project Understanding | Presentation about Project understanding | Creation of Virtual Environment | Introduction to Tech Tools | Project Presentation Session | Revised Python Concepts | Revised OOPS Concepts | Overview of Prompt Engineering | AI, Data Science, GEN AI | LLM Fundamental and Groq API key creation | Groq API Hands on implementation | Packages and workflow milestone 2 | Demo Codes Revision | Packages Revision
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Tammina Varaha Venkata Prasad | Understood about the project,LLM and Executed demo codes | Done |  | Project overview | Presentation about Project | Creation of Virtual Environment | introduction to Tech Tools required for this project | Project Presentation Session | Practised Python Concepts | Revised previous concepts | overview about prompt engineering | AI, Data Science, GEN AI,fundamentals of LLM | Learned about LLM and Groq API key | Hands on implementation of Demo code | Packages and workflow milestone 2 | Revised Prompt Engineering | Practiced Demo codes
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Gulsan Ram | Understood about llm | Done |  | Project overview | PRESENTATION ABOUT THE PROJECT | Creation of Virtual Environment | introduction to Tech Tools required for this project | Project Presentatiion Session | Practise Python Concepts | Revised previous concepts | Prompt Engineering | Ai,DataScience,GenAi,fundamentals of llm | Learned about LLM and Groq API key | Groq API Hands on implementation | Packages and workflow milestone 2 | Revised all previous | weekly revision
2 |  | LLM For Contract Analysis | Nov 25th | Dec 9th | Sujit Yadav | Understood about LLM and executed,project | Done |  | Project Understanding | Presentation about project | creation of virtual Environment | Introduction to Tech Tools | Project Presentation Session | Revised Python Concepts and project overveiw | Revised Virtual Environment | Prompt Engineering | Ai,DataScience,GenAi,fundamentals of llm | About LLM and How to generate API key from Groq API | Groq API Hands on implementation | Package Concepts and workflow | Revision -Packages | revision and hands on practice
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Tanisha Bhardwaj |  | Done |  | Overview of Project | Presented the project statement | learnnt about creation of virtual Environment | Intro to tech tools to work with | Project presenting Session | Practised Python Concepts and overviw of project | Revision of previous concepts | learnt about the prompt engineering and its use cases | learnt about Ai,DS,Gen Ai ,fundamentals of llm | About llm and Groq API | hands on implementation | about package concepts using examples and workflow | Revised all the previous concepts done | revision and hands on practice
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Sai Amar Durgesh Kopparapu | Understood About The LLM and Execution of the Demo Codes | Done |  | Overview about the project | Presentation about the project | Created the Virtual Environment for our project | Introduction of the Tech Tools for the Project | Project Presentation Session | Revision of all the fundamentals | Revision of previous concepts | Introduction and Overview of Prompt Engineering | AI, DS and Gen AI & Fundamentals of LLM's | About LLM and API Key generation from Groq | Hands on implementation of Groq API | Package Concepts and workflow topic | Revision | Revision and hands on practice
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Rudraprasad Khatua | Understood about LLM and Executed demo codes | Done |  | Overview about the project | Presentation about the Project Introduction | Created virtual Environment for our Project | Introduction of Tech tools | presentation of Project | Revision | Practice | Prompt Engineering explanation | Fundamentals of LLM, GEN AI, Data Science | Creation of groq API Key | Hand on Implimentation of Groq API | Package Concepts and workflow topic | Revision | Revision and hands on practice
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Yashovardhan Thopte | Understood about LLM and Executed demo codes | Done |  | Project overview | Project Presentation | how to createVirtual Environment in detail | Introduction of Tech tools | presentation of Project | Revision | Practice and Revision | Prompt Engineering | Fundamentals of LLM, GEN AI, Data Science | Groq API | Explanation and Execution of Demo codes | Package and Workflow for Milestone 2 | Weekly Revision | Weekly revision + Practice
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Omkar Gaware | Understood about LLM and Executed demo codes | Done |  | Project Understanding | Presentation about Project understanding | how to createVirtual Environment in detail | Introduction of Tech tools | interactive session about project understanding | Revised Concepts about Python | Practiced Python Concepts | overview about prompt engineering | DS, AI, and Gen AI | LLM Fundamentals and Groq API key | Explanation and Execution of Demo codes | Package and Workflow for Milestone 2 | Revision -Packages | revision and hands on practice
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Atmakuri Bhuvanesh | Understood about LLM and executed project | Done |  | Nov 24th: Overview of project; Nov 25th: Project Presentation; Nov 26th: how to createVirtual Environment in detail; Nov 27th: Introduction to tech tools; Nov 28th: Presentation of project; Nov 29th: Revised; Nov 30th: Practiced Python Concepts
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Manini Ojha | Understood about LLM and executed project | Done |  | Project Overview | Presentation about Project understanding | Created virtual Environment for our Project | Introduction to Tech tools | Project Understanding | Revised Concepts about Python | Practiced Python Concepts | Prompt Engineering | AI, DS and Gen AI & Fundamentals of LLM | About LLM and API Key generation from Groq | Groq API Hands on implementation | Package and Workflow for Milestone 2 | Revision | revision and hands on practice
[9 empty] | 8th Dec | 9th Dec | 10th Dec | 11th Dec | 12th Dec | 13th Dec | 14th Dec | 15th Dec | 16th Dec | 17th Dec | 18th Dec | 19th Dec | 20th Dec | 21st Dec
3 |  | Clause Identifi cation and Risk Analysis Engine | Dec 10th | Dec 24th | Sunkara Bhanu Pavan Kalyan | Understood about the LLM and execution of the project | Done |  | learnt about the workflow and project structure | learnt about the extracting text to pdf | learnt about the overlapping and left over part of the text to pdf extraction | discussed about the cleaning the clauses and chunking | learnt about the clause identification and extraction | tested the coding part and learnt from that codes | tested the coding part and learnt from that codes | discussion of the assignment | leart about the risk engine analysis and the code implementation and execution | learnt about how to run pipeline codes and introduction for regulatory update tracking | practised milestones | learnt about the regulatory update tracking | done the assignment 1 | worked on the assignments
3 |  | Clause Identifi cation and Risk Analysis Engine | Dec 10th | Dec 24th | Tanisha Bhardwaj | Understood about the LLM and hands on execution of the project | Done |  | Overview of the workflow and project structure | understanding of Workflow and extracting text to pdf | Extraction of text from pdf and Overlapping Concept | bried understanding about Cleaning the clauses and chunking | Understanding about clause identification and extraction | revision of previous topics and hands on implementation | brief revision about lama model and llm revision | delivery of assignment content and brief discussion about that | discussion on risk engine analysis and hands on implementation | discussion on run and pipeline Codes and brief Intro for Regulatory Update Tracking | Practise of both milestones 1 and 2 | Regulatory update Tracking | Practice and Assignment 1 (Task1-2) | worked on both tasks
3 |  | Clause Identifi cation and Risk Analysis Engine | Dec 10th | Dec 24th | Yashovardhan Thopte | Understood about the LLM and execution of the project | In Progress |  | Workflow and Project Structure | Text extraction and Manipulation | Text extraction and overlaps | Clause Identification | Clause Identification & Extraction | Revision | Revision | Discussed about the assignment | Risk Analysis Engine | discussion on run and pipeline Codes and Intro for Regulatory Update Tracking | Practise of both milestones 1 and 2 | Regulatory update Tracking` | Practice and Assignment 1 | Assignment 1
3 |  | Clause Identification and Risk Analysis Engine | Dec 10th | Dec 24th | Siddireddi Shanmukha Sanjana | Understood Clause Extraction and Risk Analysis Engine | Done |  | Workflow and Project Structure | Workflow and Text Extraction from pdf | Text Extraction and Overlapping | Clause Identification and Chunking | Clause Extraction | Revision on Clause Extraction | Revision on Chunking | Discussed about the assignment | Risk Analysis Engine | run & Pipeline Code and Intro on Regulatory Update Tracking | Practiced milestones 1 and 2 | Regulatory update Tracking | Worked on Assignment 1 | Worked on Assignment 1
3 |  | Clause Detection & Risk Analysis Engine | Dec 10th | Dec 24th | Deepak Sharma | Understood about LLM and execute project | in Progress |  | Workflow and Project Structure | understanding workflow and extracting text from pdf | Text Extraction and Overlapping | Clause Identification | Clause Identification | Revision | Revision | Discussed about the assignment | Risk Analysis Engine | Pipeline Codes and Regulatory Update Tracking | practised milestones | Regulatory update Tracking | Worked on assignment | Worked on assignment
|  | Clause Detection & Risk Analysis Engine | Dec 10th | Dec 24th | Chinthala Keerthi | understood clause extraction and risk analysis | done |  | Workflow and Project Structure | understanding workflow and extracting text from pdf | Learnt about text extraction and overlapping | learnt and understood about cleaning the clauses and chunking | Understanding about clause identification and extraction | revised previous session topics | practiced previous session topics | Discussed about the assignment | learnt about the risk engine analysis and hands on implementataion | discussion on run and pipeline Codes and Intro for Regulatory Update Tracking | practiced on milestones | regulatory updatw tracking | worked on assignment 1 | worked on assignme
3 |  | Clause Detection & Risk Analysis Engine | Dec 10th | Dec 24th | Sujit Yadav | understood clause extraction and risk analysis | Done |  | Workflow and Project Structure | understanding workflow and extracting text from pdf | Learnt about text extraction and overlapping topic | Clause Identification | Understanding about clause identification and extraction | Revised Session | Practiced previous session topics | Discussed about the assignment | learnt about the risk engine analysis and hands on implementataion | discussion on run and pipeline Codes and Intro for Regulatory Update Tracking | Practised milestone1 and milestone 2 | Regulatory Update Tracking | Pratice and Execution | worked on Assignment 2
3 |  | Caluse Detection & Risk Analysis Engine | Dec 10th | Dec 24th | TamminaVarahaVenkata Prasad | Understood about LLM and execution of the project | Done |  | Overview about workflow and Project Structure | Understanding about Extraction of clauses from pdf | Learnt about text extraction and overlapping | Understanding about Cleaning the clauses and chunking | Understanding about clause identification and extraction | Revised extraction and chunking topics | Revised this week topics | Discussed about the assignment | Discussion on risk engine analysis and hands on implementation | discussion on run and pipeline Codes and Intro for Regulatory Update Tracking | Practised milestone1 and milestone 2 | Regulatory Update Tracking | Worked on Assignment task 1 | Worked on Assignment task 2
3 |  | Clause Identification and Risk analysis engine | Dec 10th | Dec 24th | Rohith Vunna | Understood about clause extraction and risk analysis | Done |  | Overview about workflow and Project Structure | Overview about workflow and Project Structure | learnt about Text extraction and overlapping concept | cleaning and chunking clauses | learnt about Clause extraction and storing them | Revised extraction and chunking topics | Revised this week topics | Discussed on completion and submission of assignments & cleared some of ours queries | discussed on risk analysis engine and introduction to hands on implementation | Understood about run.py and pipeline.py codes and introduction about regulatory update tracking | practiced on milestones | Regulatory update tracking | worked on assignment tasks | worked on assignment tasks
3 |  | Clause Identification and Risk analysis | Dec 10th | Dec 24th | Dodde Raju | Understood about LLM and execute project | Done |  | workflow and Project Structure | Workflow and Text Extraction | Extraction of text from pdf and Overlapping Concept | Clause Identification and Chunking | Clause Identification and Extraction | Revision on Extraction and Chunking | Practiced previous session topics | Discussed about the assignment | Risk Analysis Engine and Hands on Implementation | Pipeline Codes and Regulatory Update Tracking | Practised millestone 1 and milestone 2 | Regulatory Update Tracking | Worked on assignment task 1 | Worked on assignment task 2
3 |  | Clause Identification and Risk analysis Engine | Dec 10th | Dec 24th | Rudraprasad Khatua |  | In Progress |  | 8th Dec: Workflow and Project Structure; 9th Dec: Understood about Text Extraction from pdf; 10th Dec: Extraction of text from pdf and Overlapping Concept
3 |  | Clause Detection & Risk Analysis Engine | Dec 10th | Dec 24th | Domakonda Anirudh | Understood LLM and executed project | Done |  | Workflow and Project Structure | Understanding about workflow and text extraction | Text Extraction and Overlapping | Introduction to Clause Identification | learnt about Clause extraction and storing them | Revision | Revised the topics covered this week | Discussed about the assignment and cleared the queries of the team members | Risk Analysis Engine | discussion on run and pipeline Codes and Intro for Regulatory Update Tracking | practiced on milestones | Regulatory Update Tracking | worked on assignment 1 | Worked on assignment
3 |  | Clause Identification and Risk Analysis Engine | Dec 10th | Dec 24nd | Charishma Maliga | Understood clause extraction and risk analysis with some sample contracts | Done |  | Discussed about Project Structure | Discussed pdf Extraction | Discussed Overlapping Concept | Introduction to Clause Identification | Discussed Clause Extraction | Revised the topics covered this week | Revised the topics covered this week | Discussed about the assignment and cleared the queries of the team members | Risk Analysis Engine | Discussed run and pipeline Codes, Intro for Regulatory Update Tracking | Practised milestone 1 and milestone 2 | Regulatory Update Tracking | Worked on assignment | Worked on assignment
3 |  | Clause Detection & Risk Analysis Engine | Dec 10th | Dec 24th | Tanishq Navsariwala | Understood clause extraction and risk analysis with some sample contracts | Done |  | Overview about workflow and Project Structure | Overview about workflow and Project Structure | Text Extraction and Overlapping | Introduction to Clause Identification | Discussed Clause Extraction | Revised the topics covered this week | Revised the topics covered this week | Discussed about the assignment and cleared the queries of the team members | Risk Analysis Engine | Discussed run and pipeline Codes, Intro for Regulatory Update Tracking | Practised milestone 1 and milestone 2 | Regulatory Update Tracking | Worked on assignment | Worked on assignment
|  | clause Detection and Rusk Analysis Engine | Dec 10th | Dec 24th | Gulsan Ram | understood about llm | Done |  | overview about workflow and project structure | workflow and Text Extraction | overlapping concept | introduction to clause identification | discussed clause Extraction | Revised on Extraction and chuking | Revised | Disussed about Assignment | Risk Analysis Engine | Discussed run and pipelibne codes | Practised milestone 1 and 2 | Regulatory update Tracking | Worked on assignment | Worked on assignment
3 |  | Clause Detection & Risk Analysis Engine | Dec 10th | Dec 24th | Atmakuri Bhuvanesh | Understood LLM and executed project | IN progress |  | 8th Dec: Overview about workfloe and project structure; 9th Dec: Workflow and text extraction; 10th Dec: Overlapping concept; 12th Dec: Clause extraction; 13th Dec: Revised on Extraction and chuking; 14th Dec: Revised; 15th Dec: Discussed about Assignment
3 |  | Clause Detection & Risk Analysis Engine | Dec 10th | Dec 24th | Omkar Gaware | Understood LLM and executed project | In progress |  | Overview about workflow and Project Structure | Workflow and Text Extraction | Extraction of text from pdf and Overlapping Concept | Clause Identification and Chunking | Clause Identification & Extraction | Revision on Text Extraction | Revision on Chunking | Discussed about the assignment | Risk Analysis Engine | Pipeline Codes and Regulatory Update Tracking | Practised milestone1 and milestone 2 | Regulatory Update Tracking | worked on assignment tasks | worked on assignment tasks
|  | Clause Detection & Risk Analysis Engine | Dec 10th | Dec 24th | Moitrayan Nath | Understood LLM and executed project | Done |  | Overview about workflow and Project Structure | Workflow and Text Extraction | Extraction of text from pdf and Overlapping Concept | Clause Identification and Chunking | Clause Identification & Extraction | Revision on Text Extraction | Revision on Chunking | Discussed about the assignment | Risk Analysis Engine | discussion on run and pipeline Codes and Intro for Regulatory Update Tracking | Practise of both milestones 1 and 2 | Regulatory Update Tracking | Worked on assignment task 1 | Assignment 1
3 |  | Clause Detection & Risk Analysis Engine | Dec 10th | Dec 24th | Sai Amar Durgesh Kopparapu | Understood LLM and executed project | Done |  | Overview about workflow and Project Structure | Workflow and Text Extraction | Extraction of text from pdf and Overlapping Concept | Clause Identification and Chunking | Clause Identification & Extraction | Revision on Text Extraction | Revision on Chunking | Discussed About the assignment | Risk Analysis Engine | Pipeline Codes and Regulatory Update Tracking | Practice on Milestone 1 and Milestone 2 | Regulatory Update Tracking | Worked on Assignment Task 1 | worked on assignment tasks
3 |  | Clause Detection & Risk Analysis Engine | Dec 10th | Dec 24th | Manini Ojha | Understood LLM and executed project | Done |  | Overview about workflow and Project Structure | Workflow and Text Extraction | Extraction of text from pdf and Overlapping Concept | Clause Identification and Chunking | Clause Identification & Extraction | Revision on Text Extraction | Revision on Chunking | Discussed about the assignment | Risk Analysis Engine | Pipeline Codes and Regulatory Update Tracking discussion | Practise of both milestones 1 and 3 | Regulatory Update Tracking | worked on assignment tasks | Worked on assignment
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Charan |  | In Progress |  | 2026-12-25 | Dec 27rth | Dec 28th | Dec 29th | 2026-12-30 | 2026-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Moitrayan Nath | Update tracking and Contract Modification | Done |  | Worked on Assignment | Discussed about Assignment Progress | Learnt about Regulatory update Tracking theoretically | Executed demo1 code and Delivering the Assignment Understanding by team members | Executed demo 2 & 3 codes and completed "building the regulatory update tracking" | revised pevious topics | practiced demo codes | contract modification and ammendment | Milestone 3 Revision | Implemented of Milestone 3 codes | Practised Milestone 3 demo codes | FeedParser and Milestone 3 execution | Slack Integration | Practised Milestone3
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Charishma Maliga | Understood Regulatory Update Tracking System and Contract Modification with codes | Done |  | Practised and Understood the working of assignment code | Discussed about Assignment Progress | Understood about Regulatory Update Tracking System | Executed demo1 code and Delivering the Assignment Understanding by team members | Discussed demo2 and demo3 codes | Discussed the progress of team members | practised milestone2 | Discussed about Contract Modification and Amendent Engine | Revised milestone3 topics | Implemention of milestone3 code | Practised Milestone3 demo codes | Discussed about FeedParser and Milestone3 code execution | Slack Integration | Practised Milestone3
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25nd | Jan 8th | Siddireddi Shanmukha Sanjana | Understood Regulatory Update Tracking System & Contract Modification | Done |  | Worked on Assignment | Assignment Presentation | Regulatory Update Tracking System | Regulatory Update Tracking System and Assignment Presentation | Executed Demo 2 & 3 codes and Bulding the Regulatory Update Tracking | Discussed the progress | Practiced Demo codes | Contract Modification and Ammendment Engine | Revised Milestone 2 | Implementation of Milestone 3 | Revised Milestone 3 Codes | FeedParser and Milestone 3 execution | Slack Integration | Practised Milestone3
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 22nd | Jan 5th | Sunkara Bhanu Pavan Kalyan | Understood Regulatory Update Tracking System and Contract Modification with codes | Done |  | checked the running of the assignments | assignment presentation | Learnt about regulatory update tracking in detail | learnt about the execution of demo1 code and assignment task delivery | learnt the executed demo2 and demo3 codes and regulatory update tracking | skimmed the concept of regulatory update tracking | recapped the milestone 3 code base | learnt about the contract modification and ammendment engine | went through ammendment engine | learnt about the milestone3 | codes practise | Learnt about FeedParser and Milestone 3 execution | Done Slack Integration | Practiced on slack integration
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Chinthala Keerthi | Understood Regulatory Update Tracking System and Contract Modification with codes | Done |  | Practiced assignment | Discussed about Assignment Progress | Learnt about Regulatory update Tracking theoretically | Executed demo 1 code and assignment presentation | discussed demo2 and demo 3 codes | discussed the progress | practiced demo codes | contract modification and ammendment | revised milestone 3 topics | implementation of milestone3 code | practised milestone 3 demo codes | FeedParser and executed milestone-3 codes | Slack integration | Practiced on slack integration
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Rohith Vunna | Update tracking and contract modification | Done |  | Practiced assignment | assignment presentation | Learnt about Regulatory update Tracking theoretically | Executed demo 1 code and assignment presentation | Executed demo 2 & 3 codes and completed "building the regulatory update tracking" | revised about previous topics | practiced milestone-3 demo codes | Discussed about Contract Modification and Amendent Engine | Revised on milestone 3 topics and codes | Implemented of Milestone 3 codes | Practised Milestone 3 demo codes | discussed on feedparser and alternations for Milestone 3 codes limitations | learnt about Slack integration | Practiced on slack integration
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Tanisha Bhardwaj | Update tracking and contract modification | Done |  | Practising over both tasks | Assignment presentation | Bried understanding about Regulatory update Tracking | Studied about regulatory update Tracking System and Assignment presentation | Executed demo 2 & 3 codes and understood building the regulatory update tracking | skimmed the concept of regulatory update tracking | practiced milestone-3 demo codes | Revision of previous modules | revised milestone 3 topics | Hands on with milestone 3 | Milestone 3 practicsed | FeedParser and executed milestone-3 codes | Hands on implementation of slack integration | Practise of Slack Integration
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Yashovardhan Thopte | Understood Regulatory Update Tracking System & Contract Modification | In Progress |  | Assignment Practice | Assignment presentation | Regulatory Update Tracking and related information | Executed demo 1 code and assignment 1 presentation | Executed demo 2 & 3 codes and completed "building the regulatory update tracking" | Pervious topics Revision | Practiced milestone-3 demo codes | contract modification and ammendment | Milestone 3 Revision | Milestone 3 Implementation | Milestone 3 Practice | FeedParser and Milestone 3 execution | Slack integration | Slack integration practice
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Gulsan Ram | update tracking and contract modification | done |  | Practising over both tasks | Discussed about assignment presentation | learnt about Tracking and related information | Regulatory update Tracking System and Assignment presentation | Executed demo 2 and 3 code and building | previous topic revision | Practiced milestone-3 demo codes | Contract Modification and Ammendment Engine | Revised Milestone3 topics | Implementation of milestone 3 code | Practised Milestone 3 demo codes | FeedParser and Milestone 3 execution | slack integration | practise of slack integration
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Tammina Varaha Venkata Prasad | Understood Regulatory Update Tracking System &Contract Modification | Done |  | Working of Assignment | Discussed about assignment presentation | Learnt about Regulatory Update Tarcking System | Regulatory update Tracking System and Assignment presentation | Executed demo 2 & 3 codes and understood building the regulatory update tracking | Revised Previous session topics | Practiced milestone-3 demo codes | Contract Modification and Ammendment Engine | Revised Milestone3 topics | Implementation of milestone 3 code | Practised Milestone 3 demo codes | FeedParser and Milestone 3 execution | Slack Integration | Practiced on slack integration
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Sujit Yadav | Update tracking and contract modification | Done |  | Assignment Practice | Discussed about assignment presentation | Regulatory Update Tracking and related information | Regulatory update Tracking System and Assignment Presentation | Executed demo 2 & 3 codes and understood building the regulatory update tracking | Discussed the progress and Revision | Practiced milestone-3 demo codes | Contract Modification and Ammendment Engine | Revised Milestone3 topics | Implementation of milestone 3 code | Practised Milestone 3 demo codes | FeedParser and Milestone 3 execution | Slack Integration | Practiced on slack integration
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 22nd | Jan 8th | Dodde Raju | Update tracking and contract modification | Done |  | Practiced assignment | Discussed about assignment presentation | Learnt about Regulatory Update Tarcking System | Studied about regulatory update Tracking System and Assignment presentation | Executed demo 2 & 3 codes and completed "building the regulatory update tracking" | Previous topics Revision | Practiced milestone-3 demo codes | Contract Modification and Ammendment Engine | Milestone 3 Topics Revision | Milestone 3 Implementation | Milestone 3 Revision | FeedParser and Milestone 3 Execution | Slack Integration | Slack integration practice
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 22nd | Jan 8th | Deepak Sharma | Update tracking and contract modification | done |  | Practiced assignment | Discussed about Assignment Progress | Regulatory Update Tracking and related information | Executed demo 1 code and assignment presentation | Executed demo 2 & 3 codes and completed "building the regulatory update tracking" | Previous topics Revision | Practiced milestone-3 demo codes | Contract Modification and Ammendment Engine | Milestone 3 Revision | Milestone 3 Implementation | Milestone 3 Revision | FeedParser and Milestone 3 Execution | Slack Integration | Slack integration practice
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 22nd | Jan 8th | Tanishq Navsariwala |  | in progress |  | Assignment Practice | Discussed about Assignment Progress | Regulatory Update Tracking and related information | Studied about regulatory update Tracking System and Assignment presentation | Executed demo 2 & 3 codes and completed "building the regulatory update tracking" | Previous topics Revision | Practiced milestone-3 demo codes | Contract Modification and Ammendment Engine | Milestone 3 Topics Revision | Milestone 3 Implementation | Milestone 3 Revision | FeedParser and Milestone 3 Execution | Slack Integration
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 22nd | Jan 8th | Omkar Gaware | Update tracking and contract modification | in progress |  | Practiced assignment | Discussed about Assignment Progress | Regulatory Update Tracking and related information | Regulatory update Tracking System and Assignment Presentation | Executed demo 2 & 3 codes and understood building the regulatory update tracking | Discussed the progress | Practiced Demo Codes from Milestone 3 | Contract Modification and Ammendment Engine | Revised Milestone3 topics | Implementation of milestone 3 code | Practised Milestone 3 demo codes | FeedParser and Milestone 3 Execution | Slack Integration | Practiced on slack integration
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 22nd | Jan 8th | Domakonda Anirudh |  | In progress |  | Practiced assignment | Discussed about Assignment Progress | Learnt about Regulatory Update Tarcking System | Regulatory update Tracking System and Assignment presentation | Executed demo 2 & 3 codes and understood building the regulatory update tracking | Discussed the progress | Practiced Demo codes | Contract Modification and Ammendment Engine | Revised Milestone 3 topics | Implemention of milestone3 code | Milestone 3 Revision | FeedParser and Milestone 3 Execution | Slack Integration | Practised Milestone 3
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 22nd | Jan 8th | Manini Ojha |  | In progress |  | Practiced assignment | Discussed about Assignment Progress | Learnt about Regulatory Update Tarcking System | Regulatory update Tracking System and Assignment presentation | Executed demo 2 & 3 codes and understood building the regulatory update tracking | Discussed the progress | Practiced Demo codes from milestone 3 | Contract Modification and Ammendment Engine | Revised Milestone 3 topics | Implemention of Milestone 3 code | Revision | FeedParser and Milestone 3 Execution | Slack Integration | Implemented Slack Integration
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 22nd | Jan 8th | Sai Amar Durgesh Kopparapu |  | In progress |  | practiced tasks | Discussed about Assignment Progress | Learnt about Regulatory Update Tracking System | Regulatory update Tracking System and Assignment presentation | Executed demo 2 & 3 codes and understood building the regulatory update tracking | Discussed the progress | Practiced Demo Codes from Milestone 3 | Contract Modification and Ammendment Engine | Revised Milestone 3 topics | Implementation of Milestone 3 code | Revision | FeedParser and Milestone 3 Execution | Slack Integration | Implemented Slack Integration

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7