## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
|  | 1 | Foundations required for doing project
|  | 2 | LLM for Contract analysis
|  | 3 | Clause Identification and Risk Analysis Engine
|  | 4 | Update tracking and Contract Modification
Note on F1: ====== ID#AAABv6zxcdw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
]
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | DDd
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 |  | Foundations required for doing project | Nov 10th | Nov 24th | Moitrayan Nath | Learnt about fundamentals required for the project | Done |  | Introductory Session | Python and Jupyter Installation done | Python keywords and Naming Conventions | Python Variables | Python Data Types | Revision | Revision | Range, Mutable and Immutable, conditional Flow control | Flow controls and functions | Functions with return keyword, Arguments and its types | Python Modules | OOPS Concepts | Constructor and Instance variables | Revision
|  | Column1 | Column2 | Column3 | Column4 | Column5
2 |  | LLM for Contract Analysis | Nov 25th | Dec 9th | Moitrayan Nath | Understood about Project, executed some demo codes. | Done |  | Project Understanding | Presentation about project | Virtual Environment Creation | Introduction to Tech Tools | Project Presentation | Revised Concepts about Python | Practiced concepts of this week | Prompt Engineering | DS, AI, and Gen AI | Learned about LLM and implemented Groq_key open source | Explanation and Execution of Demo codes | Packages and Workflow for next Milestone | Revision Package | Revised Packages
3 |  | Clause Detection & Risk Analysis Engine | Dec 10th | Dec 24th | Moitrayan Nath | Understood LLM and executed project | Done |  | Overview about workflow and Project Structure | Workflow and Text Extraction | Extraction of text from pdf and Overlapping Concept | Clause Identification and Chunking | Clause Identification & Extraction | Revision on Text Extraction | Revision on Chunking | Discussed about the assignment | Risk Analysis Engine | discussion on run and pipeline Codes and Intro for Regulatory Update Tracking | Practise of both milestones 1 and 2 | Regulatory Update Tracking | Worked on assignment task 1 | Assignment 1
4 |  | Regulatory Update Tracking System & Contract Modification | Dec 25th | Jan 8th | Moitrayan Nath | Update tracking and Contract Modification | Done |  | Worked on Assignment | Discussed about Assignment Progress | Learnt about Regulatory update Tracking theoretically | Executed demo1 code and Delivering the Assignment Understanding by team members | Executed demo 2 & 3 codes and completed "building the regulatory update tracking" | revised pevious topics | practiced demo codes | contract modification and ammendment | Milestone 3 Revision | Implemented of Milestone 3 codes | Practised Milestone 3 demo codes | FeedParser and Milestone 3 execution | Slack Integration | Practised Milestone3
Note on D2: ====== ID#AAABv5noruQ Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABv6zxceE Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABv6zxceM Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABv6zxceY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABv6zxceU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABv6zxceA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABv5noruA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABv5noruI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABv6zxcec Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABv6zxceI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABv6zxcd4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABv6zxcd8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABv5noruM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABv5noruU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABv6zxceQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABv5noruE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABv6zxcd0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7